## Timeline 2025
XHAW5112 GROUP 1 & 2 - SEMESTER 2 - 2026 TIMELINE
|  | July | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | August | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | September | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | October | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | November | 1 | 2 | 3 | 4 | 5 | 6
|  |  | M | T | W | T | F | S | S | M | T | W | T | F |  | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W |  | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W | T | F
Group 1 | Time |  | 10 12 |  |  |  | 08 10 | [6 empty] | 10 13 |  | F: 10 13; S: PH; M: PH; F: 10 12; T: 08 10; F: 10 12 |  | 08 10 | [8 empty] | 08 10 |  |  |  |  | 10 12 | [8 empty] | PH | [22 empty] | 10 12
| Sessions |  | 2 |  |  |  | 2 | [6 empty] | 3 |  | F: 3; F: 2; T: 2; F: 2 |  | 2 | [8 empty] | 2 |  |  |  |  | 2 | [31 empty] | 2 | [22 empty] | 24
Group 2 | Time |  |  | 15 17 | [5 empty] | 15 17 | [5 empty] | M: 10 12; W: 15 17; T: 15 17; F: 13 15; M: 10 12 |  | 13 15 | [5 empty] | 15 17 | [6 empty] | 15 17 | [21 empty] | 15 17 | [6 empty] | 15 17
| Sessions |  |  | 2 | [5 empty] | 2 | [5 empty] | M: 2; W: 2; T: 2; F: 2; M: 2 |  | 2 | [5 empty] | 2 | [6 empty] | 2 | [21 empty] | 2 | [6 empty] | 2 | [26 empty] | 24
| Week # |  | 1 | [6 empty] | 2 | [5 empty] | M: 3; M: 4; M: 5; M: 6; M: 7 | [7 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [7 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [7 empty] | 16
| Milestone |  | Introduction | [6 empty] | Task 1 | [5 empty] | M: Task 2 | [28 empty] | Task 3
| Activity |  | Laying the foundation | [6 empty] | Phase 1 - Investigate and report on your design of a webpage and mobile application (Individual) | [5 empty] | M: Phase 2 - Form groups and roles. Select the best logo, web page and mobile app design (Group); M: Phase 3 - Select the best logo, colour scheme and idea ¦ Design the Mobile App and the Website (Group); M: Phase 1 - Complete Wireframes (Group); M: Phase 2 - Develop the Mobile Application (Group) | [21 empty] | Phase 3 - Develop the Website (Group) | [6 empty] | Phase 1 - Complete development of the Website (Group) | [21 empty] | Phase 2 - Presentation, Slides, Video (Group) | [6 empty] | Phase 3 - Peer Evaluation (Individual) | [7 empty] | Phase 4 - Report (Individual)
| DETAILS OF THE ACTIVITY |  | • Introduction to each of the following: o Professional Conduct in the Workplace o WIL Manual; o Project requirements o Project design specifications; o Presentation specifications. • Explain the importance of: o Participation of the students; o Attendance of the students; o Responsibilities of the students; o Milestones/deliverables. • Groups of a maximum of three members must be established. | [6 empty] | • Write a report on your idea of a web page and mobile application based on the chosen scenario. Motivate why you have chosen your client and define user centered design. Include a colour palette and design a logo for your client. | [5 empty] | M: • Review the requirements for the project; • Select the best web page and mobile app design based on each team member’s submitted report or include a combination of all of the designs into the final planning for the project; • Allocate tasks to various members of the group.; M: The group must do the following: • Review the requirements for the project. • Select the best idea, colour scheme and logo design based on each team members report or include a combination of all and create a combined logo design/colour scheme. • Research on mobile applications and website designs. • Document infrastructure that will be used throughout the project • Use FIGMA to design low-fidelity wireframes for the mobile application and website; M: • Using FIGMA design high-fidelity wireframes for the mobile application and website. (Include all screens, colour, images, logo, detail, information etc.); M: • Develop the mobile application. • Code the application and align the look, feel and functionality to your wireframes. • The code for your project must be worked on in your GitHub repository. (Lecturer to provide the GitHub link) | [21 empty] | • START developing the website. (not completing in this part) • Complete HTML. • The code for your project must be worked on in your GitHub repository. (Lecturer to provide the GitHub link) | [6 empty] | • Complete the development of the website. • Complete CSS and JavaScript aspects. • Code the website and align the look, feel and functionality to your wireframes and mobile application. • Publish the website. | [21 empty] | Presentation and demonstration of your project, to your WIL co-ordinator and peers. Create a detailed video presentation and explain the processes and design, all group members to be involved, talk/show faces. Each individual member of the group must demonstrate and explain a section of the project. • The presentation must begin with the PowerPoint slide show and include a motivation for why the design was selected. • Demonstrate the functionality of the web page and the mobile app. The above is for the video and in person presentation | [6 empty] | Complete the peer-evaluations (one for each group member) | [7 empty] | Submit the final report which contains Part 1, Part 2 and Part 3. Subheading for Updates should be included here if anything was updated from Task 1 and Task 2, explain this in detail and highlight it throughout the document that it stands out.
| DUE |  | COMPLETE READING OF THE OFFICIAL MODULE MANUAL | [6 empty] | COMPLETE DESIGN DOCUMENTS DETAILING ALL CHOICES TO COLOUR, FUNCTIONALITY, FEATURES, ETC. OF THE WEBSITE AND MOBILE APPLICATION - SUBMISSION PROCESS WILL BE DISCUSSED IN CLASS | [5 empty] | M: MILESTONE 3 (COMPLETED MOBILE APPLICATION + DEVELOP WEBSITE CONTENT)(SUBMISSION PROCESS WILL BE DISCUSSED IN CLASS) | [28 empty] | COMPLETED WEBSITE + PRESENTATION + VIDEO RECORDING OF PRESENTATION | [36 empty] | SUBMISSION OF ALL DOCUMENTATION